## Sheet1
| Project Start Date: | 2026-01-06 | [5 empty] | 2026-01-13 |  |  |  | 2026-02-10 |  |  |  | 2026-03-10 |  |  |  |  | 2026-04-14
| Project Name: | Real-Time Market Sentiment and Volatility Tracking |  |  |  |  | Week starting: | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28
# | Activity | Assigned To | Start | End | Days | Status | %Done
1 | Research & Design | Michael | 2026-01-06 | 2026-01-13 | 6 | Complete | 100%
2 | Evn. Setup | Michael | 2026-01-13 | 2026-01-20 | 3 | Complete | 100%
3 | Data Ingestion | Michael | 2026-01-20 | 2026-01-27 | 4 | In progress | 70%
4 | Processing I | Michael | 2026-02-03 | 2026-02-10 | 4 | Not started | 0%
5 | Midterm Report | Michael | 2026-02-17 | 2026-02-24 | 4 | Not started | 0%
6 | Processing II | Michael | 2026-03-03 | 2026-03-10 | 4 | Not started | 0%
7 | Storage | Michael | 2026-03-17 | 2026-03-24 | 4 | Not started | 0%
8 | Refinement | Michael | 2026-03-24 | 2026-03-31 | 4 | Not started | 0%
9 | Final Report | Michael | 2026-03-31 | 2026-04-07 | 4 | Not started | 0%
10
Not started
In progress
Blocked
Complete
Formulas:
Start = [End, row above]
Days = IF([End]="","",NETWORKDAYS([Start],[End]))